## 工作表1
Task | Begin | End | Topics | Person
1 | 5-22-2019 | 6-4-2019 | Object detection (tracking) | Walter, Scott
2 |  |  | integrate code with backend app | Walter, Scott
3 | 5-22-2019 | 5-28-2019 | Front-end web app | Jason, Wayne
4 |  |  | face-recognition for login | Jason, Wayne
5 | 5-22-2019 | 5-28-2019 | Back-end web app | Jason, Wayne
6 | 5-28-2019 | 5-31-2019 | Voice call during vision test
7 | 5-28-2019 | 5-31-2019 | issue LINE message
8 | 6-1-2019 | 6-10-2019 | System integration
9 |  |  | integrate with sub-system
10 | 6-5-2019 | 6-10-2019 | Integration test
11 | 5-28-2019 | 6-10-2019 | PPT writing | Scott, and all